## PCSCC -OLD
| Updated Date : 7 Mar 2018 |  |  | —— Latest update
| Issues for discussion-PCSCC | Priority | Timeline | Status | Update - 07/03/2018 | Checking - 07/03/2018
1 | Student Module:
1) | withdraw: need 2 dates: 1)withdraw submission date and 2)student's last day in the centre; 3)withdraw reasons: provide a drop down list; all 3 fields are compulsory; | High |  | Nathalie to provide standard reasons - Replied on 24 Feb 2018 via wechat | Done
2) | Finance
| Create: add ”create CN“ | Medium |  |  | Done
| View Invoice: default setting is to filter out the outstanding invoices only; -Please remove the default filtering and show all the invoices of the student. | High |  |  | Done
| View Deposit: please add button to view "deposit" record | High |  |  | Done | if use fin_hq account , no "Depoist" Button under view & create
| View All: only shows the invoice listing, normally shall show inovices and all receipts etc. | Low |  |  | Switching via Tabs, already done
| Apply subsidy module: Service type is wrong, seems like this section follows the childcare calculation. For student care, there is only one program type. Please double check | High |  |  | Done, fixed to Half Day Care (PM) for Student Care
3) | Medical information/Emergency Medical Treatment/Enrollment Document Confirmation: needs to be updated or hide first | Low | 2018-03-25 |  | Pending, to double confirm the medical info & documents
4) | Parents: <---- should change name to "Family" (It should included parent ,sibling , grandpa , grandmother etc. information) | Low
| Set some fields as compulsory-Name/IC/Mobile/home address/email address/primary guardian/nationality | High |  |  | Done | - Id Type should "NRIC/FIN/PASSPROT“， NRIC should changed to " ID No." - How to add information above 3 Peoples ?
5) | Students:
| Set some fields as compulsory-Name/Birth Cert/nationality/PR status | High |  | Nathalie to double check wehter birthe cert length fixed - Replied on 23 Mar 2018 via wechat | Done, to add in auto verification for Birth Cert when filling the form & importing data | - "Household Income" information to be hided - ID type " Parents' IC?" to be removed
| Service type: Half Day Care (AM) is wrong. -For all: Student Care Type: Student Care Service; Program Type: Half Day (PM) | Medium |  |  | Done | Fix service type to Half Day (PM)
| Prior experience in pre-school：irrelavent, please hide or remove | Medium |  |  | Done
| Subsidy information: SCFA/SUG. Please show this subsidy under student profile section | Medium |  |  | Done | No information show under " Subsidy Info"
| Add "IC/Birth Cert" as the search criteria | High |  |  | Done
6) | 如果学生是兄弟姐妹且都在Nascas Student Care Centre的话 系统需自动link information to each other. | Medium | 2018-03-18 |  | Pending
| 在输入父母信息进行查询时，系统也能显示出Sibling 的信息 | Medium | 2018-03-18 |  | Pending
2 | Subsidy module:
1) | subsidy amount doesn’t tally with payment advice (value date: 16/1/2018); As agreed, payment advice is the final version to be followed. | High |  | Nathalie to double check the taidii subsidy payment listing with the payment advice - checked, no difference | Done
2) | Subsidy status monitoring function?-from application till approval | High | 2018-03-11 | Nathalie to provide 1) subsidy control listing 2) email tempalte to submit subsidy - Replied on 26 Feb 2018 via wechat | Haven't received the email template so far; Modifyinge subsidy application procedure now
3 | Auto offset advance payments with invoices: does the system have the function currently? | High |  | To generate and pending centre approval | Done
4 | Finance Module
1) | Invoice
| Show remark in the page directly, instead of click the button | Medium |  |  | Done | ok
| 是否可以显示付款在invoice listing 的界面 | Medium |  | resolved | Done | ok
| 未关账前允许修改发票（仅限HQ finance） | Medium | 2018-03-11 |  | Working on it now
| 不允许centre开多个item的发票 ， 开票规则已在2018年3月5日发送在wechat上 | Medium | 2018-03-11 |  | Pending
| Add filter of "scfa" or non-scfa student, so that to create batch invoice seperately | Medium
2) | Advance payment
| 允许按类别分开列出金额在一张Adv Payment 上 | Medium |  |  | First phase done, limiting to one Sales Item per ADV for centre account-Done
| 允许advance payment可以用于offset其他sales item的invoice-该功能仅限于HQ finance | Medium |  |  | Done, HQ Finance can modify the Sales Item at any time to enable the usage of ADV on other Sales Items
| 未关账前允许修改预付款（仅限HQ finance） | Medium | 2018-03-18 |  | Working on it now
| 添加Reversal 功能 | Medium
3) | Receipt
| 未关账前允许修改收款以及offset（仅限HQ finance） | Medium | 2018-03-18 |  | Working on it now
| 确保receipt date 如果早于Invoice date时 系统不允许生成receipt voucher | Medium |  |  | Done
| Offset ADV/OVP是否能显示明细 | Medium |  |  | Done, showing Valid From & Valid For info in the list now
| 如果收到excess amount for subsidy ，如何输入excess部分？ | Medium |  |  | Input the full amount and Subsidy OVP to be generated automatically, to verify the Subsidy OVP and show list of Subsidy OVPs | To separate the listing of Subsidy OVP
| 不允许centre开多个发票的收据，一张收据只对应一张发票 | Medium | 2018-03-11 |  | Pending
| 添加Reversal 功能 | Medium
4) | Credit Note
| 是否可以显示付款在CN listing 的界面 | Medium |  |  | Done
| 未关账前允许修改credit note（仅限HQ finance） | Medium | 2018-03-18 |  | Working on it now
| 针对存货项目的CN，需要加入Qty的数据 | High | 2018-03-30
5) | 缺少Adjustment 模块 （ eg. Tranfer adv payment from A student to B student ,classfiy to Bad Debt, etc) | Medium |  |  | Pending, to double confirm the design of Adjustment Note and modify accordingly
6) | Refund
| 未关账前允许修改refund（仅限HQ finance） | Medium | 2018-03-18 |  | Working on it now
| 无法做partial refund | Medium |  |  | Done
| 如果我们refund 给家长,后来由于某种原因,这张refund没有成功，该如何处理？（如果refund 做在1月份， 而在2月份关账后才得知refund没有成功） | Medium | 2018-03-18 |  | Pending, to use adjustment note, adjusting Refunded OVP/ADV/DEP & BANK | Reverse refund
| 添加Reversal 功能 | Medium
7） | OVP
| 如果void CN,那由于这张CN而生成的OVP会自动void掉吗？ | Medium |  |  | Yes, Done
| 不允许centre offset OVP- Subsidy | Medium | 2018-03-11 |  | Pending
| 添加Reversal 功能 | Medium
8) | 进入ALL的界面进行操作 ，做完操作后是否能依旧返回到ALL的界面 ？ | Low |  |  | Done
5 | Report function
1) | Transaction report for a certain period, ie, for the month; (same as Taidii transaction report) | High | 2018-03-11 |  | Template confirmed, working on it now
2) | Listing of outstanding invoices/deposits/Advance Payment /OVP as at a certain date | High | 2018-03-18 |  | Pending, tempaltes to be confirmed
3) | AR Aging (Details & Summary) as at a certain date | High | 2018-03-18 |  | Pending
4) | Student's SOA as at a certain date | Medium | 2018-03-25 |  | Pending
5) | Student's attendance report for a certain period | Medium | 2018-03-25 |  | Pending
6) | Student Outstanding Analysis Report -(separate due from parent & due from govt) | High | 2018-03-18 |  | Use the Invoice listing to be finished
7) | Item invoice ,lnvoice listing and receipt Report for a certain period | Medium | 2018-03-25 |  | Pending
6 | Enrollment Module
1） | 设置学生入学流程，强制新注册学生支付registration fee/deposit/school fee and/or 1 month advance fee; | Medium | 2018-03-18 |  | Pending
2） | 新学生如果不交registration fee/deposit，则需提交SCFA application form and SUG form | Medium | 2018-03-18 |  | Pending
3) | 允许上传相关文件，比如“幼儿出生证明，家长身份证明件等 | Medium | 2018-03-18 |  | Pending
7 | Invoice Template
1） | Not able to create and save a template | High | 2018-03-11 |  | Shall be working, to doulbe confirm
2) | How to set auto | High | 2018-03-11 |  | To show how to set the auto invoice
8 | Monthly GIRO deduction report | High | 2018-03-25 |  | Pending, referring to the txt file to be uploaded to Bank portals?
| Monthly GIRO collection import to system and auto generate receipts by batch | High | 2018-03-25
9 | Others
1) | 允许同时开多个页面 | Medium | 2018-03-25 |  | Pending
2)
10 | Info Module
| 需要添加下面两个接送情况 | Medium
| a) 经父母许可，学生自己回家 |  | 2018-03-18 |  | Pending
| b) 父母临时找人来接送孩子，需要提供接送人的名字，IC 以及联系号码 |  | 2018-03-18 |  | Pending, to add Temporary Pick-up Person recording function
11 | Staff Module
| 需要添加额外信息- 详情在wechat中发送，发送日期为 2018年3月5日 | Low | 2018-03-18 |  | Pending
12 | Reminders (student attendace(<50% twice a month), subsidy expiring, others…) | Medium | 2018-03-25 |  | Pending
| Auto send inovices/receipts/reminders-1st/2nd/3rd to Parent | Medium
13 | 关于SCFA-pending的学生，期初导入和1-3月份已经注册了，直接输入需要强制填写的信息（如subsidy申请的期间，submission date，estimated scfa/SUG amount）？
14 | Withdraw Module
Centre 填写学生withdraw的信息并offset 该学生的ADV/OVP/DEP ,HQ 确认withdraw 学生的信息以及centre输入的单据，随后做相应的后续处理（eg. Refund/close student account etc.)
Offset 的顺序 ：ADV -> OVP->DEP
特殊情况：
- SUG Student withdraw without 1 month notice.
- SUG Student withdraw with 1 month notice.
(4月中旬以后 Apply SCFA/Renewal SCFA/Withdraw SFCA student都要在网上申请)
15 | 建立Nascans @ Rubikon (RBKSCC)的账户
RBKSCC 的权限问题 以及培训
16 | 数据导入问题
导入数据若出现收款是offset下一个月的发票的话，这类receipt改成ADV PAYMENT,起effective date 为收款当天
17 | 数据检查的问题
Report设置好之后， 数据处理人员需同Taidii 生成的Report 先条条核对一遍再交给HQ检查 。交由HQ检查后，若有系统逻辑改动等会影响到检查过后的文件，需及时通知HQ,以便加快核对的速度。
18 | Holiday Surcharge Module
Summary
| Invoice modification, nett discount modification |  | 2018-03-11
| Reports of high priority, voucher modification for all, pick-up related changes, sibling info, staff info, enrollment & withdrawn process |  | 2018-03-11
| Reports of medium priority, ADV modification, Reminder module |  | 2018-03-25
*Please note the timeline is the ideal situation. It may be delayed for one or two weeks depending on the problems encountered during the R&D process

## RBKSCC & CCKSCC
Issues for discussion-RBKSCC & CCKSCC
|  | Priority | New Priority | Timeline | Status
1 | Finance Module
1-1 | Invoice
| 允许一张invoice开多个sales items | High |  |  | 已完成
1-2 | Advance Payment
| 允许中心一次性输入多条不同sales item的advance payment | High |  |  | 已完成;需测试installment是否会自动offset可用的invoices;查一下谁有权限confirm pending receipts
| 添加Reversal 功能 | Medium |  |  | 先void或者开credit note来处理
1-3 | Receipt
| 允许中心可以在一张receipt上选多张invoices | High |  |  | 已完成，目前仅开放给PCSCC；需改成开放给所有中心
| 添加Reversal 功能 | Medium
1-4 | Deposit
| 添加Reversal 功能 | Medium
1-5 | Refund
| 添加Reversal 功能 | Medium
2 | Sales Item Management
| Sales Item太多，选起来很容易选错， 是否可以弄的更直观和便于选取 | High | 1 |  | 这个取决于HQ对于sales item的分类和整理；我们可以相应改造sales item下拉列表；需按照Price Listing页做相应的整理
| 中心希望可以修改sales item的价格 ，但是如果完全放开，担心会照成sales item的混乱，关于这块前期有和Justin讨论，放开部分给centre， sales item 还是由HQ create， centre允许可以对部分sales item的价格进行修改 （eg. Basketball fee ,etc.) | High |  |  | 待讨论；先确认哪些Sales Item放开，并且先建立好Sales Item，只允许centre修改价格；另外关于Sales Item需要在invoices上显示的日期，有待确认根据什么规则来计算prorated price
3 | Voucher Model
| 中心发放voucher给家长，在规定的期限里，学生注册并支付费用时，可用于抵扣 | Medium |  |  | 待讨论，目前是在payment method里有增加voucher这一项，需要填写voucher no.;需和marketing确认voucher的发放和使用限制后再决定如何做voucher管理模块
4 | Uploaded Giro Deduction file function | Medium
| RBKSCC 2018年9月开始 当月的monthly fee全部用GIRO Deduction， 这块由财务部自己做 Giro Deduction upload的 file ， centre不再提供excel file给finance to upload Giro Deduction | High |  |  | 仍然可以先用目前的方式，提供excel文件给我们手动转换为txt file；让centre确认哪些invoice需要做GIRO Deduction的那部分功能，以及根据选择的invoices自动产生银行需要的txt file尚在开发中
5 | Discount Module
| Centre 的价格变化比较频繁 导致discount的金额越来越多 ，是否可以有个module，centre 可以对学生设置不同sale item的discount，但需要approve后 才可以生效 | High | 2 |  | 需要改造现有的discount manager模块，让centre可以新增并分配该discount到其中心，由HQ来批准；但之后仍然需要centre去为学生申请这些折扣，然后由cluster head来批准

## New Invoice - sample
September '18 INVOICE For Student XXXXXX
Nascans Student Care Centre @ XXXXXX
Sept'18 Monthly Fee = $ 260.00
Exhibition Material Cost = $ 8.90
Prepaid = $ | ***This refers to adv, ovp
Pending (prev month) = $ | ***total OS before 1Sep's new inovice
======================================
Total Due = $ 268.90 | ***Total OS as of 1 Sep
Kindly Note: Student Statement Of Accounts and new invoices are enclosed for your reference. All fees are due by 5th of this month.
1. For GIRO payment, the deduction will be made on 5th of each month;
2. For cheque payment, all cheque should be crossed and make payable to : NASCANS PTE LTD
3. For Bank Transfers, please transfer to: | Only show VA account information after Jan2019, otherwise, show centre bank account for now
Account Name: Nascans Pte Ltd
Account No.: 86021301000211
Bank Name: United Overseas Bank
Bank Code: 7375
Branch: Main branch
Branch Code: 001
Currency: SGD
4. Payment of fees, if nett of subsidy, for whatsoever reason, if subsidy is different from what is stipulated in the invoice, Centre reserves the right to request the shortfall for the balance.
In case you have already made payment, we thank you for your prompt action and kind support.
Warm Regards,
Nascans Student Care Centre @ XXXXXX
This is a computer generated Invoice and hence needs no signature.
If you have any enquries, please email to XXXSCC@nascans.com.